## Sheet1
Project: | A BEHAVIOURAL BIOMETRICS BASED ON STYLOMETRICS IN CLOUD COMPUTING DOMAIN FOR CYBERCRIME DETECTION
Project Planner
A legend describing the charting follows: | [5 empty] | Done |  | In Progress |  | Not Started |  | Planned Duration
ID | Current Status | Task description | Duration | Start Date | Estimated Finished Date | Finish Date | Predecessor Tasks | Resource Names | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 | Period 7 | Period 8 | Period 9 | Period 10 | Period 11 | Period 12 | Period 13 | Period 14 | Period 15 | Period 16 | Period 17 | Period 18 | Period 19 | Period 20 | Period 21 | Period 22 | Period 23 | Period 24 | Period 25 | Period 26 | Period 27 | Period 28 | Period 29 | Period 30 | Period 31 | Period 32 | Period 33 | Period 34 | Period 35 | Period 36 | Period 37 | Period 38 | Period 39 | Period 40 | Period 41 | Period 42 | Period 43 | Period 44 | Period 45 | Period 46 | Period 47 | Period 48 | Period 49 | Period 50 | Period 51 | Period 52 | Period 53 | Period 54 | Period 55 | Period 56 | Period 57 | Period 58 | Period 59 | Period 60
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1000 |  | Stylometric Research Paper |  | 2018-04-01 | 2018-10-31
1001 |  | Research Proposals |  | 2018-04-01 | 2018-04-30
1002 |  | Gather sources for literature review |  | 2018-04-01 | 2018-04-20
1003 |  | Build Research timeline |  | 2018-04-13 | 2018-04-15 | 2018-04-15
1004 |  | Identifying research area |  | 2018-04-20 | 2018-04-21
1005 |  | Crafting the problem statement |  | 2018-04-20 | 2018-04-20
1006 |  | Literature Review |  | 2018-04-20 | 2018-04-28 |  | 1002
1007 |  | Conducting first draft of literature review |  | 2018-04-20 | 2018-04-22
1008 |  | Review Draft Literature Review |  | 2018-04-22 | 2018-04-22
1009 |  | Enhance Literature Review Cycle |  | 2018-04-22 | 2018-04-26
1010 |  | Conduct draft of Literature Review |  | 2018-04-22 | 2018-04-22
1011 |  | Review current draft of Literature Review |  | 2018-04-22 | 2018-04-22
1012 |  | Conduct Final Literature Review |  | 2018-04-27 | 2018-04-28
1013 |  | Conduct Introduction |  | 2018-04-28 | 2018-04-28
1014 |  | Draft Methodolgy |  | 2018-04-28 | 2018-04-28
1015 |  | Review Methodology |  | 2018-04-29 | 2018-04-29
1016 |  | Construct final Methodolgy Draft |  | 2018-04-29 | 2018-04-29
1017 |  | Convert from word to latex |  | 2018-04-30 | 2018-04-30
1018 |  | Project Report |  | 2018-05-01 | 2018-10-31 |  | 1001
1019 |  | BTBD
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030